GPRTool

Development Master Plan

Version 1.0  —  March 2026

Target completion: mid-June 2026

Boon Lay Ong  —  Curtin University, Perth WA

# Overview

GPRTool is a browser-based CAD application for calculating Green Plot Ratio (GPR) — the urban greenery planning metric invented by Boon Lay Ong. It enables architects and planners to model a site, place vegetation, and generate a verified GPR calculation and PDF report.

This document is the master development plan for GPRTool V1. It records all decisions made to date, defines the phase structure and daily targets, and serves as the primary context anchor for AI-assisted development sessions.

## Technology Stack

All decisions are final for V1 unless noted otherwise.

| Component | Decision |
| --- | --- |
| Geometry kernel | Pure Python (shapely + numpy). No OCCT for V1. |
| Backend | Python + FastAPI, deployed as Vercel serverless functions |
| Frontend / 3D | Three.js (browser-native, no build step) |
| Database | Supabase (PostgreSQL) |
| Deployment | Vercel (frontend + API), GitHub for version control |
| Architecture | PWA, browser-first, no auth for V1 |
| PDF generation | ReportLab (Python, server-side) |
| Plant data | Curated 100-species starter set from TRY / ORNL DAAC sources |
| UI style | Century Gothic, GPR brand palette, lean codebase |

## V1 Scope

GPRTool V1 delivers five user-facing capabilities in sequence:

•  Draw a site boundary polygon and calculate its area

•  Draw a building footprint, set floors and height, view 3D massing

•  Define landscape zones and place plants from a curated species database

•  Calculate GPR (total leaf area / site area) with a breakdown by plant type

•  Generate and download a formatted PDF report

File import (DXF/IFC), user authentication, and advanced geometry operations are deferred to V2.

## Phase Summary

| # | Phase | Key deliverable | Days | Week |
| --- | --- | --- | --- | --- |
| 0 | Pre-work sprint | Repo, deploy pipeline, UI skeleton, fiddly bits resolved | 7 | 1 |
| 1 | Site boundary | Draw polygon, calculate area, display in 3D | 5 | 2 |
| 2 | Building massing | Footprint, floors, height, 3D extrusion | 6 | 2–3 |
| 3a | Landscape zones & plants | Zone polygons, plant placement UI, species picker | 6 | 3–4 |
| 3b | Plant database | Curate 100 species from existing data, load to Supabase | 4 | 4 |
| 3c | Wire plant UI | Connect placement UI to live plant database | 2 | 4–5 |
| 4 | GPR calculation | LAI formula, calculation engine, results display | 6 | 5–6 |
| 5 | Supabase persistence | Save/load projects, store GPR results | 6 | 6–7 |
| 6 | PDF report | Formatted report, plant schedule, download | 8 | 7–8 |
| 7 | UI polish | Brand palette, Century Gothic, responsive layout | 8 | 8–9 |
| 8 | Testing & hardening | Edge cases, browser testing, error handling | 8 | 9–10 |
| 9 | Buffer & launch | Slippage, final deploy, soft launch | 12 | 10–12 |

Total: approximately 78 working days — target completion mid-June 2026.

| Phase 0 — Pre-work sprint | 7 days | Week 1 |
| --- | --- | --- |

Purpose

Phase 0 is not feature development. Its sole purpose is to eliminate every source of friction before serious programming begins. When Phase 0 is complete, the programming phases should flow without setup surprises, configuration puzzles, or architectural second-guessing.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 1 | New repo + Vercel | Create GPRTool GitHub repo. Connect to Vercel. Confirm a placeholder page deploys successfully. Set up deploy.bat. |
| Day 2 | Python on Vercel proven | Write a minimal /api/health Python function. Confirm it deploys and responds on Vercel. Resolve any requirements.txt or runtime version issues. |
| Day 3 | Supabase schema | Create Supabase project. Design and create tables: sites, buildings, zones, plants, species, gpr_results. No code yet — just the schema, confirmed working. |
| Day 4 | UI skeleton | Strip GPRToolDemo of all non-essential code (alarm, DesktopAI remnants). Agree on final panel layout: header, left panel, 3D viewport, right panel, footer. Build the skeleton HTML/CSS only — no functionality. |
| Day 5 | Polygon drawing proof | Prove Three.js polygon click-to-draw works in an isolated test canvas. This is the riskiest UI interaction — test it before Phase 1 depends on it. |
| Day 6 | GPR formula on paper | Write out the complete GPR calculation by hand with a sample project. Verify the formula, units, and LAI logic before writing a single line of Python. Produce GPRTOOL_CONTEXT.md first draft. |
| Day 7 | Plant data review | Open LAI Database (Combined).xlsx. Identify the 100 best candidate species for V1. Produce a shortlist CSV. Do not load to Supabase yet — just agree the list. |

Exit criteria

•  A live Vercel URL returning a working page

•  Python API function confirmed working on Vercel

•  Supabase schema created and documented

•  UI skeleton agreed and committed

•  Polygon drawing behaviour understood

•  GPR formula verified on paper

•  100-species shortlist CSV produced

•  GPRTOOL_CONTEXT.md written

| Phase 1 — Site boundary drawing | 5 days | Week 2 |
| --- | --- | --- |

Purpose

The user draws a site boundary polygon on the canvas. The backend calculates its area. The result is displayed. This is the first real GPR input and the first end-to-end data flow in the tool.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 8 | 2D draw mode | Activate 2D top-down view. User clicks to place polygon vertices. Visual feedback on each click (dot + line preview to cursor). |
| Day 9 | Close polygon | Double-click or click first vertex to close the polygon. Polygon fills with a semi-transparent colour. Vertices remain editable (drag to move). |
| Day 10 | Area calculation | Send polygon coordinates to Python backend. Calculate area using shapely. Return area in m². Display in right panel. |
| Day 11 | 3D view switch | Switch from 2D draw mode to 3D perspective view. Site boundary renders as a flat plane at ground level. Camera orbit works around it. |
| Day 12 | Polish & save | Clear / redraw workflow. Store site polygon coordinates in Supabase sites table. Confirm round-trip save/load works. |

Exit criteria

•  User can draw a site polygon by clicking

•  Area displays correctly in m²

•  3D view shows the site as a ground plane

•  Site data saves and loads from Supabase

| Phase 2 — Building massing | 6 days | Weeks 2–3 |
| --- | --- | --- |

Purpose

The user draws a building footprint within the site, sets the number of floors and floor-to-floor height, and sees a 3D massing model. This establishes the non-landscape area of the site.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 13 | Footprint drawing | In 2D mode, draw a building footprint polygon within the site boundary. Distinguish visually from the site boundary (different colour). |
| Day 14 | Floor inputs | Right panel inputs: number of floors, floor-to-floor height (m). Calculate total building height. Display GFA (gross floor area) as a bonus metric. |
| Day 15 | Backend extrusion | Send footprint + height to Python backend. Use shapely to validate and return extrusion data. Three.js renders the 3D box massing. |
| Day 16 | 3D scene composition | Site boundary as ground plane + building massing as extruded solid in the same scene. Correct materials, lighting, shadows. |
| Day 17 | Multiple buildings | Support placing more than one building on the site. Each building is a separate object, independently editable. |
| Day 18 | Save & load | Store building footprint, floors, and height in Supabase buildings table. Load restores the full 3D scene. |

Exit criteria

•  Building footprint draws within the site

•  3D massing renders correctly from floor/height inputs

•  Multiple buildings supported

•  Scene saves and loads from Supabase

| Phase 3 — Landscape zones, plants & database | 12 days | Weeks 3–5 |
| --- | --- | --- |

Purpose

This is the most complex phase. The user defines green zones within the site, places plants within those zones, selects species from the curated database, and sees the planted areas in 3D. Runs in three sub-phases.

Phase 3a — Landscape zones & plant placement UI (Days 19–24)

| Day | Goal | Detail |
| --- | --- | --- |
| Day 19 | Zone polygons | Draw landscape zone polygons within the site, outside building footprints. Zone area calculated and displayed. |
| Day 20 | Plant placement | Click within a zone to place a plant marker. Plant rendered as a simple 3D symbol (sphere or cone). Multiple plants per zone. |
| Day 21 | Species picker | Right panel species picker: search by name, filter by type (tree/shrub/groundcover). Shows LAI and canopy spread. |
| Day 22 | Assign species | Select a plant marker then assign a species from the picker. Plant symbol updates to reflect canopy spread. LAI stored per plant. |
| Day 23 | Edit & delete | Select and delete individual plants. Move plant markers by dragging. Reassign species. Clear zone. |
| Day 24 | Save zones & plants | Store zones, plant positions, and species assignments in Supabase zones and plants tables. Load restores full planted scene. |

Phase 3b — Plant database curation (Days 25–28)

| Day | Goal | Detail |
| --- | --- | --- |
| Day 25 | Audit source data | Open LAI Database (Combined).xlsx and source files. Identify usable records. Flag duplicates, missing LAI, missing canopy spread. |
| Day 26 | Curate 100 species | Select 100 species: ~25 trees, ~25 shrubs, ~20 groundcovers, ~10 turf/grass, ~10 climbers/epiphytes, ~10 palms. Verify LAI from TRY/ORNL sources. |
| Day 27 | Produce plants.csv | Clean and format the 100-species CSV: scientific_name, common_name, type, lai, canopy_spread_m, source, notes. |
| Day 28 | Load to Supabase | Import plants.csv into Supabase species table. Confirm all records load correctly. Test a species query from the API. |

Phase 3c — Wire plant UI to live database (Days 29–30)

| Day | Goal | Detail |
| --- | --- | --- |
| Day 29 | API endpoint | Python /api/species endpoint: returns species list, supports search and type filter. Test in browser. |
| Day 30 | Connect picker | Replace any hardcoded plant data in the UI with live API calls. Confirm species picker shows real data. End-to-end test of full placement flow. |

Exit criteria

•  Landscape zones draw within the site, outside buildings

•  Plants place within zones and display in 3D

•  Species picker queries live Supabase data

•  100 curated species loaded and queryable

•  Full scene saves and loads from Supabase

| Phase 4 — GPR calculation engine | 6 days | Weeks 5–6 |
| --- | --- | --- |

Purpose

The core metric. GPR = total leaf area / site area. The engine aggregates leaf area across all placed plants using LAI and canopy spread, then divides by the site area. The result is displayed with a full breakdown.

The GPR formula

For each plant: leaf area = LAI × canopy area (m²). Canopy area = π × (canopy_spread / 2)² for trees and shrubs. For groundcovers and turf: leaf area = LAI × zone area covered. GPR = sum of all plant leaf areas / site area.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 31 | Calculation endpoint | Python /api/calculate endpoint. Accepts site area, list of plants with species data. Returns total leaf area and GPR value. |
| Day 32 | Per-plant breakdown | Return breakdown: leaf area per plant, subtotals by plant type (trees, shrubs, groundcovers, turf). Display in right panel. |
| Day 33 | Live recalculation | GPR recalculates automatically whenever plants are added, removed, or reassigned. Display updates in real time. |
| Day 34 | GPR target indicator | Show a simple indicator against a configurable target GPR (e.g. 0.5 minimum). Green if met, amber if close, red if below. |
| Day 35 | Store results | Save GPR calculation results to Supabase gpr_results table with timestamp. Link to the project. |
| Day 36 | Validation & edge cases | Test: no plants placed, single plant, all turf, all trees, very large site, zero site area. Confirm no crashes or incorrect results. |

Exit criteria

•  GPR calculates correctly for all plant types

•  Breakdown by plant type displays

•  Recalculates live on any change

•  Results store to Supabase

•  Edge cases handled gracefully

| Phase 5 — Supabase persistence | 6 days | Weeks 6–7 |
| --- | --- | --- |

Purpose

Full project save and load. A user can name a project, save the complete scene (site, buildings, zones, plants, GPR results), close the browser, return later, and reload exactly where they left off.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 37 | Project model | Define project as a container linking site, buildings, zones, plants, and gpr_results. Add project_id foreign keys to all tables if not already present. |
| Day 38 | Save project | Save Project button. Prompts for project name. Saves all scene data to Supabase in a single transaction. Confirms success. |
| Day 39 | Load project | Projects list panel or dropdown. Select a project to load. Restores full 3D scene from Supabase data. |
| Day 40 | New / clear project | New Project clears the scene and resets all inputs. Confirm dialog to avoid accidental loss. |
| Day 41 | Project metadata | Store project name, date created, date modified, site address (text field). Display in header or panel. |
| Day 42 | Round-trip test | Full end-to-end test: create project, place full scene, save, reload in new browser tab, verify every element restores correctly. |

Exit criteria

•  Projects save and load completely

•  New project clears scene safely

•  All scene elements survive a round-trip to Supabase

| Phase 6 — PDF report | 8 days | Weeks 7–8 |
| --- | --- | --- |

Purpose

The primary output for professional use. A formatted PDF containing project details, site area, building summary, plant schedule table, GPR result, and a rendered site plan image. Generated server-side with ReportLab, downloadable in one click.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 43 | ReportLab setup | Install and test ReportLab on Vercel. Confirm a minimal PDF generates and downloads correctly. Resolve any Vercel serverless constraints. |
| Day 44 | Report layout | Design the report page layout: cover block, project metadata, site summary, plant schedule table, GPR result block. No content yet — just layout. |
| Day 45 | Site plan image | Capture the Three.js viewport as a PNG (renderer.domElement.toDataURL). Send to backend. Embed in PDF. Confirm image quality. |
| Day 46 | Plant schedule table | Generate plant schedule: species, common name, type, quantity, LAI, canopy spread, leaf area contribution. Formatted as a table in the PDF. |
| Day 47 | GPR result block | GPR result prominently displayed with breakdown by plant type. Target GPR indicator. Simple bar or visual indicator of GPR vs target. |
| Day 48 | Cover & metadata | Project name, site address, date, GPR value on cover page. Designer name / firm as optional field. |
| Day 49 | Download endpoint | Python /api/report endpoint. Assembles full PDF from project data. Returns as downloadable file. Test download in browser. |
| Day 50 | Polish & review | Review full PDF end-to-end. Typography, spacing, alignment. Test with a realistic project. Adjust as needed. |

Exit criteria

•  PDF generates and downloads in one click

•  Plant schedule table is accurate and complete

•  Site plan image embeds correctly

•  GPR result is clearly presented

•  Report looks professionally formatted

| Phase 7 — UI polish & UX | 8 days | Weeks 8–9 |
| --- | --- | --- |

Purpose

Transform the functional tool into a professional product. Typography, brand palette, responsive layout, feedback messages, loading states, and overall visual quality. GPRTool should look like a purpose-built professional application.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 51 | Brand palette | Define GPR colour palette (greens, neutrals, accent). Apply consistently across header, panels, buttons, and viewport background. |
| Day 52 | Century Gothic | Apply Century Gothic throughout the UI: headings, labels, inputs, status messages. Confirm web font loading or system font fallback. |
| Day 53 | Header & navigation | Final header design: GPRTool logo, project name display, save/load controls. Clean and compact. |
| Day 54 | Panel layout | Left panel (tools/commands), right panel (properties/results), collapsible. Confirm usable on a 1366×768 laptop screen. |
| Day 55 | Input controls | Style all number inputs, dropdowns, buttons consistently. Clear visual distinction between active/inactive states. |
| Day 56 | Feedback & loading | Loading spinners during API calls. Status bar messages. Error states for failed API calls. Success confirmation for saves. |
| Day 57 | 3D viewport quality | Lighting, shadows, material quality. Plant symbols legible at typical zoom levels. Site and building colours visually distinct. |
| Day 58 | Responsive review | Test on 1920×1080, 1366×768, and mobile viewport. Fix any layout breaks. Mobile is secondary — desktop is primary. |

Exit criteria

•  Century Gothic applied throughout

•  Brand palette consistent across all UI elements

•  Tool is usable and clear on a 1366×768 laptop

•  Loading and error states communicate clearly

| Phase 8 — Testing & hardening | 8 days | Weeks 9–10 |
| --- | --- | --- |

Purpose

Systematic testing of the full tool. Edge cases, cross-browser behaviour, error handling, and performance on a realistic project. The goal is a tool that does not crash or produce incorrect results in normal professional use.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 59 | GPR edge cases | No plants placed, single plant, all one type, zero canopy spread, very large LAI values. Confirm all produce sensible results or clear error messages. |
| Day 60 | Geometry edge cases | Very small site, site boundary self-intersecting, building outside site boundary, overlapping buildings. Confirm validation and error messages. |
| Day 61 | API error handling | Simulate Supabase connection failure, Vercel timeout, malformed request. Confirm graceful degradation and user-facing error messages. |
| Day 62 | Chrome testing | Full workflow test in Chrome. Note and fix any rendering or behaviour issues. |
| Day 63 | Edge & Firefox testing | Full workflow test in Edge and Firefox. Fix any cross-browser issues. |
| Day 64 | Performance test | Test with a realistic large project: 500m² site, 3 buildings, 50 plants. Confirm no sluggishness or memory issues. |
| Day 65 | Save/load stress test | Create 5 different projects. Save all. Load each. Confirm no data mixing or corruption. |
| Day 66 | Final review | Walk through the complete user workflow from blank canvas to PDF report. Note any remaining rough edges. Fix critical issues only. |

Exit criteria

•  No crashes on edge case inputs

•  Cross-browser: Chrome, Edge, Firefox all pass

•  Error messages are clear and actionable

•  Full workflow completes without issues on a realistic project

| Phase 9 — Buffer & launch prep | 12 days | Weeks 10–12 |
| --- | --- | --- |

Purpose

Twelve days of deliberately protected time. The first priority is absorbing any slippage from earlier phases. Once all phases are genuinely complete, the remaining days are used for launch preparation.

Daily targets

| Day | Goal | Detail |
| --- | --- | --- |
| Day 67–70 | Slippage absorption | Finish any incomplete work from Phases 1–8. Do not begin launch prep until all exit criteria are met. |
| Day 71 | GPRTOOL_CONTEXT.md final | Update GPRTOOL_CONTEXT.md with final architecture, all decisions, known issues, and V2 backlog. This is the handover document. |
| Day 72 | Production deploy | Final deploy to Vercel production URL. Confirm all environment variables, Supabase connection strings, and API endpoints are correct. |
| Day 73 | Smoke test production | Run the full workflow on the live production URL. Confirm PDF downloads, Supabase writes, and 3D rendering all work in production. |
| Day 74 | Documentation | Write a simple one-page user guide. What GPRTool does, how to use it, what the GPR result means. |
| Day 75–78 | Soft launch buffer | Reserve for feedback from first users, small fixes, and anything that surfaces post-launch. Do not plan new features here. |

Exit criteria

•  All previous phase exit criteria met

•  Production URL live and fully functional

•  GPRTOOL_CONTEXT.md complete and current

•  User guide written

•  GPRTool V1 launched

# Decisions log

This section records key architectural and strategic decisions made during planning. Update with date and rationale as new decisions are made.

| Date | Decision | Rationale | Status |
| --- | --- | --- | --- |
| Mar 2026 | Geometry kernel: shapely + numpy (no OCCT) | OCCT too large for Vercel serverless. Sufficient for V1 geometry. OCCT deferred to V2. | Final |
| Mar 2026 | Deployment: Vercel (not Render) | Owner preference. Requires lightweight Python only. | Final |
| Mar 2026 | No auth for V1 | Reduces complexity. Single-user or shared-link model sufficient for soft launch. | Final |
| Mar 2026 | Plant data: 100-species curated starter set | Commercial credibility from verified sources (TRY, ORNL DAAC). Quality over quantity. | Final |
| Mar 2026 | PDF: ReportLab (server-side Python) | Full control over layout. jsPDF alternative considered but server-side preferred. | Final |
| Mar 2026 | GPR formula verified on paper before coding | Phase 0 Day 6 deliverable. Prevents formula errors propagating into code. | Planned |

# V2 backlog

Features explicitly deferred from V1. Do not implement during V1 development.

•  DXF / IFC file import for site boundary and building footprint

•  pythonocc-core / OpenCASCADE geometry kernel for complex surfaces

•  User authentication and multi-user projects

•  Shareable project URLs

•  Expanded plant database (full dataset ingestion pipeline)

•  Mobile-optimised layout

•  Mobius Module integration (GPRTool as a Tier 3 module)

•  GPR compliance checking against specific planning regulations

•  Collaborative editing

# Working notes

Use this section for session notes, observations, and anything that should be remembered but does not belong in the decisions log.

Last updated: March 2026

Development partner: Claude (Anthropic)

Repository: to be created — GPRTool (GitHub: lotr2929/GPRTool)

Vercel project: to be created

Supabase project: to be created